BNCC/DE P. 5b

2006-2007

UWI TERTIARY LEVEL INSTITUTIONS UNIT

Submission to the Board for Non-Campus Countries and Distance Education (BNCC/DE), September 25, 2006, Belize

WORK PLAN FOR THE PERIOD AUGUST 01, 2006 TO JULY 31, 2007

UWI TLI UNIT

September 6, 2006

THE UNIVERSITY OF THE WEST INDIES

TERTIARY LEVEL INSTITUTIONS UNIT (TLIU)

WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Facilitate the development of Associate Degree and Joint Bachelor’s Degree Programmes: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Assessment of Associate Degrees: Antigua and Barbuda International Institute of Technology (ABIIT). |  |  |  |  |  |  |  |  |  |  |  |  | Request received; Institution to forward course packages. |
| 1.2 | Assessment of Associate Degrees – Arts (Humanities): Barbados Community College. |  |  |  |  |  |  |  |  |  |  |  |  | (1) Recommendation submitted to BUS that: “Graduates who earn a minimum GPA of 2.5 in the following BCC Associate Degree in Arts Programme (Spanish with Themes, French with Themes and History Courses HIST 112; HIST 221; HIST 122 & HIST 222) and a grade of B in the specified courses be granted exemptions from corresponding UWI Bachelor’s degree courses”. (2) Assessment for Geography and Literature courses pending. |

UWI TLI UNIT			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Assessment of : 1. Executive Diploma in Management (EDM) and 2. Executive Development Programme (EDP) in Project Management for Matriculation to BSc Management Studies: Centre for Management Development (Cave Hill School of Business). |  |  |  |  |  |  |  |  |  |  |  |  | A meeting was convened with the Faculty of Social Sciences – Management Studies (CH) and CMD on December 12, 2005. (1) The Executive Diploma in Management (EDM) was considered by the Department of Management Studies, Cave Hill for Normal Matriculation. A cross- Campus meeting is to be convened to consider Advanced Standing. (2) The Executive Development (EDP) in Project Management has been assessed as equivalent to MGMT 3056. To be sent to BNCC/DE & BUS after concurrence with UWI Mona. (3) Follow-up meetings are planned for the current Semester. |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | Assessment of Associate Degrees – Business Studies for articulation with UWI BSc Social Sciences: H. Lavity Stoutt Community College (BVI). |  |  |  |  |  |  |  |  |  |  |  |  | (1) Course outlines and materials were received from the College. (2) Complete packages were forwarded to the Faculty of Social Sciences for Assessment. (3) Assessors’ visit to the College is planned for late September. |
| 1.5 | Assessment of Associate Degrees – Legal Studies: H. Lavity Stoutt Community College (BVI). |  |  |  |  |  |  |  |  |  |  |  |  | College to forward complete course package for Assessment for Advanced Placement. |
| 1.6 | Assessment of Associate Degrees: Dominica State College. |  |  |  |  |  |  |  |  |  |  |  |  | Initiated collaboration with relevant Deans: Dr. George Belle; Dean FSS (CH) – Accounts & Sociology Dr. Mark Figureoa; Dean FSS (M) – Economics & Sociology Dr. Hamid Ghany; Dean FSS (St. Aug) – Economics & Accounts - Requested paper assessment (course content, structure, etc.). (2) Assessors’ visit to DSC is planned for late September. |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 | Assessment of Associate Degrees - ‘Two-Plus-Two’ Articulation Arrangement with UWI leading to the BSc in Hospitality and Tourism Management: T A Marryshow Community College |  |  |  |  |  |  |  |  |  |  |  |  | The recommendation that TAMCC be permitted to offer the Hospitality and Tourism Programme in a ‘two-plus-two’ arrangement with the UWI, Cave Hill Campus has been approved by BUS, subject to certain conditions (physical infrastructure) to be met by the College. |
| 1.8 | Assessment of Associate Degrees - Business Studies, Management Information Systems, Library Technical Studies, Hospitality and Entertainment Management: Council of Community Colleges of Jamaica (CCCJ). |  |  |  |  |  |  |  |  |  |  |  |  | - Request received; arrangements with Faculties initiated. - Colleges are preparing scripts and examination papers for submission to the various Faculties in September. |
| 1.9 | Assessment of Diploma - Articulation with UWI Bachelor of Arts Degree programme offered by the Faculty of Hamanities and Education: Edna Manley. |  |  |  |  |  |  |  |  |  |  |  |  | The Faculty Assessors Report is expected in October. |
| 1.10 | Assessment of Certificate - Technical Library Studies for matriculation to UWI BA in Library and Information Studies: Excelsior Community College. |  |  |  |  |  |  |  |  |  |  |  |  | Scripts and matching examination papers have been submitted to the Department of Library Studies, Faculty of Humanities & Education for assessment. |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.11 | Monitoring of Associate Degrees: Management Institute of National Development (MIND) |  |  |  |  |  |  |  |  |  |  |  |  | Conduct tracer studeis. |
| 1.12 | Assessment of Associate Degrees - Information Technology, Business Studies, Psychology and Literatures and English: College of Science, Technology and Applied Arts of Trinidad & Tobago (COSTAATT). |  |  |  |  |  |  |  |  |  |  |  |  | - Documents to be received in September. - Paper Assessment to be conducted. - Assessors’ visit to be arranged. |
| 1.13 | Assessment of Advanced Placement: International School of Port of Spain (ISPS). |  |  |  |  |  |  |  |  |  |  |  |  | - Reports of paper assessment received from Faculty. (2) Assessors’ visit to be arranged. |
| 1.14 | Assessment of Associate Degrees – Sports Tourism: Trinidad & Tobago Institute of Hospitality & Tourism (Trinidad Campus). |  |  |  |  |  |  |  |  |  |  |  |  | - Awaiting paper assessment. - Assessors’ visit to be arranged. |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Facilitate the Franchise/Divestment of UWI Degree Courses/Programmes: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Facilitation of Certificate Programmes - Hospitality: Holy Childhood Institute. |  |  |  |  |  |  |  |  |  |  |  |  | - Initiated discussions with the Faculty of Social Sciences. (2) Arrangements for institutional assessment pending. |
| 2.2 | Facilitation of B.Sc in Public Sector Management - Level I: Jamaica Constabulary Staff College. |  |  |  |  |  |  |  |  |  |  |  |  | An Assessment exercise is to be arranged by the Faculty. |
| 2.3 | Facilitation of B.Sc in Public Sector Management - Level II: Management Institute for National Development (MIND). |  |  |  |  |  |  |  |  |  |  |  |  | - The Faculty of Social Sciences Mona has identified a number of issues. - A Joint Committee (Faculty/MIND/TLIU) has been struck to resolve issues, and agree on the way forward. |
| 2.4 | Facilitation of Social Sceinces Programme - Level I: St. Vincent & The Grenadines Community College. |  |  |  |  |  |  |  |  |  |  |  |  | (1) The recommendations for franchise arrangements were approved by the Chair of BUS. (2) To be ratified by BUS. |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MANAGE TLIU/UWI ARTICULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Conduct Needs Assessment/Institutional Visits: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Antigua & Barbuda, Belize, British Virgin Islands, Cayman Islands, Dominica, Grenada, Jamaica, Monsterrat, St. Kitts & Nevis, St. Lucia, St. Vincent & The Grenadines and Trinidad & Tobago. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Arrange Orientation workshops for TLI Staff and UWI Faculty: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Arrange orientation workshops for new staff involved in the monitoring activities at ASC, CFBC and SALCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROMOTE INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Monitor the delivery process of franchise programmes, identify the barriers to successful implementation, propose solutions and make the necessary interventions and/or recommendations to overcome such barriers. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Arrange monitoring visits as requested and funded by the Antigua State College (ASC), Clarence Fitzroy Bryant College (CFBC) and Sir Arthur Lewis Community College (SALCC). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Arrange teleconferences between UWI Faculties and ASC, CFBC and SALCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Arrange attachments of staff from ASC, CFBC and SALCC to the Cave Hill Campus. |  |  |  |  |  |  |  |  |  |  |  |  |  |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROMOTE INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | Facilitate collaboration of the UWI School of Medical Radiation Technology in the delivery of the BSc in Diagnostic Imaging Radiography. |  |  |  |  |  |  |  |  |  |  |  |  | (1) A draft Memorandum of Understanding was completed. (2) The nature of the arrangements is being discussed with the Deputy Principal at Mona. |
| 1.5 | Arrange first Semester workshop for Franchisees of the UWI Degree and Certificate programmes. |  |  |  |  |  |  |  |  |  |  |  |  | Workshops planned for November. |
| 2 | Assist with the Development of Procedures for improving Quality Assurance in Examinations for Barbados and the OECS. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Monitor the Cipriani College of Labour & Cooperative Studies franchise of the UWI Bachelor in Social Sciences Level I Programme. |  |  |  |  |  |  |  |  |  |  |  |  | Orientation scheduled for August (2006). |
| 4 | Monitor the Online Masters in Education and facilitate the participation of TLI staff from the OECS. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Collaborate with ACTI to facilitate the development of institutional quality assurance systems and accreditation, equivalencies and articulation of programmes (as required). |  |  |  |  |  |  |  |  |  |  |  |  |  |

UWI TLI UNIT 			WORK PLAN FOR THE PERIOD AUGUST 2006 – JULY 2007

| ACTIVITIES TO BE UNDERTAKEN / UNDERWAY |  | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COLLECT DATA AND CONDUCT RELEVANT RESEARCH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Human Resource Development Needs Assessment Focus Groups/Workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Barbados |  |  |  |  |  |  |  |  |  |  |  |  | Scheduled for October 16-17. |
| 1.2 | Cayman Islands |  |  |  |  |  |  |  |  |  |  |  |  | Scheduled for October 3. |
| 2. | Conduct Regional HR Development Surveys, Data Analysis and Reporting. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | Collect TLIs data for the revision of the UWI/TLI Unit Profiles of the TLIs in the Campus and Non-Campus Countries. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. | Upgrade TLIU’s Website. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. | Publication of TLIU’s Lightrays. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SPECIAL PROJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Trinidad & Tobago Non-University Tertiary Education Sector Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Revise the draft proposal as needed to secure funding. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Coordinate and manage the implementation of activities that may emanate from the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by TLI Unit

September, 2006