BNCC/DE P.11d

2006/2007

UWI TERTIARY LEVEL INSTITUTIONS UNIT

Submission to the Board for Non-campus Countries and Distance Education (BNCC/DE), May 07, 2007, BRITISH VIRGIN ISLANDS

Franchise of UWI Bachelor of Social Sciences Level I Programme to Cipriani College of Labour and Co-operative Studies

Brief:

On March 31, 2006, Professor E. Nigel Harris, Vice Chancellor of The University of the West Indies (UWI), and Dr. Roosevelt Williams, Director of the Cipriani College of Labour and
Co-operative Studies (CCLCS), signed a Memorandum of Understanding outlining the conditions whereby the CCLCS would be allowed to deliver the UWI Bachelor of Social Sciences Level I Programme commencing in the 2006/2007 Academic Year.

However, difficulties in the implementation of the programme resulted in its postponement. The new date proposed for commencement is the 2007/2008 Academic Year. To ensure the commencement of the programme at this time, a number of actions are scheduled. The actions are as follows:

1.	Advertisement of the programme and inviting persons to apply was scheduled for the 	period January to March 2007.

2.	Selection of persons for admission will be completed by CCLCS, Friday April 20, 2007 	and sent to UWI.

3.	Approval of selected candidates by UWI on or before Monday, April 30, 2007.

4.	Notification of the students of their admission to the programme will be done by CCLCS 	during the first week of May 2007.

5.	Selection and approval of staff to teach in the programme will be completed by the last 	week in May 2007.

6.	Training of some staff at UWI will be conducted during June/July 2007.

7.	Orientation of all staff will be conducted during the second week in August 2007.

The Board for Non-Campus Countries & Distance Education is being requested to note the actions being taken to ensure the start of the programme in the upcoming Academic Year 2007/2008.

UWI TLI Unit